## SUMMARY
Project ID:
Address:
No. of Floors: | 2
Building GSF | 2500
DIVISION NO. | DESCRIPTION | TOTAL DIV. COST | TOTAL DIV. COST (PER SF)
1000 | General Requirements | 14781.0784 | 5.9124
3300 | Utilities | 124945.7179 | 49.9783
PROJECTED COST |  | 139726.7964 | 55.8907
OVERHEAD AND PROFIT | 20% | 27945.3593 | 11.1781
INSURANCE | 3% | 4191.8039 | 1.6767
CONTINGENCY | 5% | 6986.3398 | 2.7945
SUGGESTED BASE BID |  | 178850.2994 | 71.5401

## MATERIAL TAKE-OFF
Project:
Address:
Scope: | UTILITIES
Date:
SR # | REF | DESCRIPTION | QUANTITY | UNIT | WASTAGE | QUANTITY W/ WASTAGE | LABOR HOURS | WAGES | TOTAL LABOR HOUR | TOTAL LABOUR COST | MATERIAL RATE | TOTAL MATETRIAL COST | EQUIPMENT RATE | TOTAL EQUIPMENT COSTS | SUB COST
01. GENERAL REQUIREMENTS
1 |  | Supervision and Coordination | 1 | LS | 0% | 1 | 37.1155 | 84.16 | 37.1155 | 3123.6429 | 0 | 0 | 0 | 0 | 3123.6429 | 124945.7179
2 |  | Submittals and Shop drawings | 1 | LS | 0% | 1 | 24.4962 | 84.16 | 24.4962 | 2061.6043 | 0 | 0 | 0 | 0 | 2061.6043
3 |  | Final Cleaning | 1 | LS | 0% | 1 | 12.6193 | 84.16 | 12.6193 | 1062.0386 | 0 | 0 | 0 | 0 | 1062.0386
4 |  | Mobilization Costs | 1 | LS | 0% | 1 | 34.8886 | 84.16 | 34.8886 | 2936.2244 | 0 | 0 | 0 | 0 | 2936.2244
5 |  | Bond @ 2% | 1 | LS | 0% | 1 | 29.6924 | 84.16 | 29.6924 | 2498.9144 | 0 | 0 | 0 | 0 | 2498.9144
6 |  | Temporary Control & Facilities | 1 | LS | 0% | 1 | 14.5493 | 84.16 | 14.5493 | 1224.468 | 0 | 0 | 0 | 0 | 1224.468
7 |  | Scaffolding | 1 | LS | 0% | 1 | 22.2693 | 84.16 | 22.2693 | 1874.1858 | 0 | 0 | 0 | 0 | 1874.1858
[14 empty] | SUBTOTAL | 14781.0784
33. UTILITIES
Manhole / Inlet Grate
8 | C-10 | Fire Hydrant | 1 | EA | 0% | 1 | 43.0125 | 77.19 | 43.0125 | 3320.1349 | 15455.1081 | 15455.1081 | 0 | 0 | 18775.243
9 |  | 18'' ADS In-Line Drain | 1 | EA | 0% | 1 | 8.2269 | 77.19 | 8.2269 | 635.0311 | 813.0796 | 813.0796 | 0 | 0 | 1448.1108
10 |  | Type C Inlet | 1 | EA | 0% | 1 | 36.6581 | 77.19 | 36.6581 | 2829.6403 | 3257.7667 | 3257.7667 | 0 | 0 | 6087.407
11 |  | M-4 Manhole (4' Dia) | 1 | EA | 0% | 1 | 54.2588 | 77.19 | 54.2588 | 4188.2395 | 5266.4505 | 5266.4505 | 0 | 0 | 9454.69
12 |  | Sanitary Manhole | 2 | EA | 0% | 2 | 54.2588 | 77.19 | 108.5177 | 8376.4789 | 5266.4505 | 10532.901 | 0 | 0 | 18909.3799
Conduits
13 |  | 4'' PVC Electrical Conduit | 123.34 | LF | 10% | 135.674 | 0.21275 | 77.19 | 28.8646 | 2228.0618 | 11.026 | 1495.9415 | 0 | 0 | 3724.0034
14 |  | 4'' PVC Telecom Conduit | 130.83 | LF | 10% | 143.913 | 0.21275 | 77.19 | 30.6175 | 2363.3641 | 11.026 | 1586.7847 | 0 | 0 | 3950.1488
Storm Pipes
15 |  | 6'' PVC Roof Drain | 63.69 | LF | 10% | 70.059 | 0.27861 | 77.19 | 19.5191 | 1506.6823 | 18.4815 | 1294.7954 | 0 | 0 | 2801.4777
16 |  | Excavation | 10.6667 | CY | 10% | 11.7333 | 0.59917 | 77.19 | 7.0303 | 542.6667 |  | 0 | 0 | 0 | 542.6667
17 |  | Backfill | 10.2 | CY | 10% | 11.22 | 0.4314 | 77.19 | 4.8403 | 373.626 |  | 0 | 0 | 0 | 373.626
18 |  | 15'' HDPE Pipe | 82.15 | LF | 10% | 90.365 | 0.69653 | 77.19 | 62.9415 | 4858.453 | 33.041 | 2985.75 | 0 | 0 | 7844.2029
19 |  | Excavation | 45.5556 | CY | 10% | 50.1111 | 0.59917 | 77.19 | 30.0251 | 2317.6389 |  | 0 | 0 | 0 | 2317.6389
20 |  | Backfill | 41.83 | CY | 10% | 46.013 | 0.4314 | 77.19 | 19.8501 | 1532.2329 |  | 0 | 0 | 0 | 1532.2329
Sanitary Pipes
21 |  | 8'' PVC San Main Line | 57.27 | LF | 10% | 62.997 | 0.37148 | 77.19 | 23.4021 | 1806.4101 | 30.192 | 1902.0054 | 0 | 0 | 3708.4155
22 |  | Excavation | 12.6667 | CY | 10% | 13.9333 | 0.59917 | 77.19 | 8.3484 | 644.4167 |  | 0 | 0 | 0 | 644.4167
23 |  | Backfill | 12.616 | CY | 10% | 13.8776 | 0.4314 | 77.19 | 5.9868 | 462.1244 |  | 0 | 0 | 0 | 462.1244
24 |  | 8'' PVC Pipe | 4.02 | LF | 10% | 4.422 | 0.37148 | 77.19 | 1.6427 | 126.7988 | 24.938 | 110.2758 | 0 | 0 | 237.0747
25 |  | Excavation | 0.88889 | CY | 10% | 0.97778 | 0.59917 | 77.19 | 0.58586 | 45.2222 |  | 0 | 0 | 0 | 45.2222
26 |  | Backfill | 0.8382 | CY | 10% | 0.92202 | 0.4314 | 77.19 | 0.39776 | 30.7033 |  | 0 | 0 | 0 | 30.7033
27 |  | 6'' PVC C-900 San. Lateral | 123.51 | LF | 10% | 135.861 | 0.27861 | 77.19 | 37.8522 | 2921.8139 | 19.943 | 2709.4759 | 0 | 0 | 5631.2898
28 |  | Excavation | 20.6667 | CY | 10% | 22.7333 | 0.59917 | 77.19 | 13.6212 | 1051.4167 |  | 0 | 0 | 0 | 1051.4167
29 |  | Backfill | 19.7654 | CY | 10% | 21.7419 | 0.4314 | 77.19 | 9.3795 | 724.0055 |  | 0 | 0 | 0 | 724.0055
Fittings
30 |  | 6'' San Sewer Connection | 2 | EA | 0% | 2 | 6.3515 | 77.19 | 12.703 | 980.5465 | 423.9599 | 847.9197 | 0 | 0 | 1828.4662
31 |  | 4'' PVC Telecom Connection | 2 | EA | 0% | 2 | 5.7235 | 77.19 | 11.4471 | 883.5986 | 345.9639 | 691.9278 | 0 | 0 | 1575.5263
32 |  | 15''x6'' Tee | 1 | EA | 0% | 1 | 15.691 | 77.19 | 15.691 | 1211.1852 | 1686.2907 | 1686.2907 | 0 | 0 | 2897.4759
33 |  | 6'' PVC Roof Drain Connection | 2 | EA | 0% | 2 | 5.3049 | 77.19 | 10.6098 | 818.9666 | 332.1999 | 664.3998 | 0 | 0 | 1483.3664
Exfiltration Trench
34 |  | Exfiltration Trench | 58.21 | LF | 10% | 64.031 | 0.6993 | 77.19 | 44.7769 | 3456.3272 | 30.5065 | 1953.3617 | 0 | 0 | 5409.6889
35 |  | Excavation | 98.8685 | CY | 10% | 108.7554 | 0.59917 | 77.19 | 65.1631 | 5029.9359 |  | 0 | 0 | 0 | 5029.9359
36 |  | Backfill | 95.143 | CY | 10% | 104.6573 | 0.4314 | 77.19 | 45.1495 | 3485.0867 |  | 0 | 0 | 0 | 3485.0867
Catch Basin / Cleanout
37 |  | Catch Basin | 2 | EA | 0% | 2 | 22.7909 | 77.19 | 45.5818 | 3518.4576 | 1916.7517 | 3833.5034 | 0 | 0 | 7351.961
38 |  | 6'' PVC Clean Out | 5 | EA | 0% | 5 | 7.9831 | 77.19 | 39.9156 | 3081.0852 | 501.5258 | 2507.6287 | 0 | 0 | 5588.7139
[14 empty] | SUBTOTAL | 124945.7179
PROJECTED COST | [14 empty] | 139726.7964
OVERHEAD AND PROFIT | [13 empty] | 20% | 27945.3593
INSURANCE | [13 empty] | 3% | 4191.8039
CONTINGENCY | [13 empty] | 5% | 6986.3398
SUGGESTED BID | [14 empty] | 178850.2994
NOTES:
General Notes: The prices used while preparing the estimate were taken from RSMeans online i.e. the standard pricing. So, it is preferred to review the prices.
|  | Note | [9 empty] | Legend
| 1 | The drawings are scaled as per the mentioned scales on the plans. | [9 empty] | LBS = Pound
SF= Square Feet
LF = Linear Feet
EA = Each
CY = Cubic Yard
SY = Square Yard
LOC = Location
LS = Lum Sum